|  |
| --- |
| Sarunu procedūras kandidātiemTo candidates of the negotiated procedure |

Ar šo Pasūtītājs izdod pielikumu Nr.1 saskaņā ar Sarunu procedūras Nr.AST2019/32 "Divu 110/21/6.3 kV 25/25/25 MVA transformatoru piegāde apakšstacijai "Olaine"" vispārīgo noteikumu punktu 11.3.

Hereby the Customer issues the addendum No.1 in accordance with paragraph 11.3. of general conditions of the negotiation procedure No AST2019/32 "The supply of two 110/21/6.3 kV 25/25/25 MVA transformers to the substation "Olaine"".

**Sarunu procedūras Nr.AST2019/32 " Divu 110/21/6.3 kV 25/25/25 MVA transformatoru piegāde apakšstacijai "Olaine"" nolikuma 1. pielikums.**

**Addendum No.1 to the regulations of negotiation procedure No.AST2019/32 "The supply of two 110/21/6.3 kV 25/25/25 MVA transformers to the substation "Olaine""**

**Grozījums Nr.1**

**Amendment No 1**

Sarunu procedūras vispārīgo noteikumu 8.3. punkts:

General conditions of the negotiation procedure Clause 8.3:

|  |  |
| --- | --- |
| 8.3. Kandidātu pieteikumi jāiesniedz līdz **2019. gada 30. aprīļa plkst. 11.00** (pēc Latvijas laika) EIS e-konkursu apakšsistēmā.  | 8.3. Candidates applications shall be submitted until **April 30,** **2019**, **before time 11.00 a.m.** (Latvian time) in the EIS e-tender subsystem.  |

tiek izteikts šādā redakcijā:

is amended as follows:

|  |  |
| --- | --- |
| 8.3. Kandidātu pieteikumi jāiesniedz līdz **2019. gada 30. maija plkst. 11.00** (pēc Latvijas laika) EIS e-konkursu apakšsistēmā.  | 8.3. Candidates applications shall be submitted until **May 30,** **2019**, **before time 11.00 a.m.** (Latvian time) in the EIS e-tender subsystem.  |

**Grozījums Nr.2**

**Amendment No 2**

Sarunu procedūras vispārīgo noteikumu 14.1. punkts:

General conditions of the negotiation procedure Clause 14.1:

|  |  |
| --- | --- |
| 14.1. Iesniegtie pieteikumi tiks atvērti EIS e-konkursu apakšsistēmā atklātā sēdē **2019. gada 30. aprīļa plkst. 11.00.** Iesniegto pieteikumu atvēršanas procesam var sekot līdzi tiešsaistes režīmā EIS e-konkursu apakšsistēmā vai personīgi Dārzciema ielā 86, Rīgā. | 14.1. The submitted applications will be opened in the EIS e-tender subsystem in an open meeting on **April 30, 2019, time: 11.00 a.m.**. It is possible to follow the process of opening of submitted applications online in the EIS e-tender subsystem or in person at the premises at Darzciema Street 86, Riga. |

tiek izteikts šādā redakcijā:

is amended as follows:

|  |  |
| --- | --- |
| 14.1. Iesniegtie pieteikumi tiks atvērti EIS e-konkursu apakšsistēmā atklātā sēdē **2019. gada 30. maija plkst. 11.00.** Iesniegto pieteikumu atvēršanas procesam var sekot līdzi tiešsaistes režīmā EIS e-konkursu apakšsistēmā vai personīgi Dārzciema ielā 86, Rīgā. | 14.1. The submitted applications will be opened in the EIS e-tender subsystem in an open meeting on **May 30, 2019, time: 11.00 a.m.**. It is possible to follow the process of opening of submitted applications online in the EIS e-tender subsystem or in person at the premises at Darzciema Street 86, Riga. |

**Grozījums Nr.3**

**Amendment No 3**

5. pielikums "Cenu saraksts" pozīcijas:

Annex 5 "Price list" positions:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Nr. No. | NosaukumsDescription | DaudzumsQuantity | Vienības cenaUnit price | Kopējā cena Total price | ValūtaCurrency | Jāpiegādā /Time schedule |
| 6. | Transformers placing on the foundations after delivery, aggregates assembly, transformers attaching to foundations, connections of secondary equipment, tests of fully assembled transformer and reports of performed tests and commissioning. | 2 units |  |  | EUR | First transformer from 01.06.2020. till 12.06.2020. |
| Second transformer from 02.10.2020. till 15.10.2020. |
| 7. | 115/21/6.3 kV 25/25/25 MVA transformer - including transformer oil and aggregates. | 2 units |  |  | EUR | First transformer from 01.06.2020. till 12.06.2020. |
| Second transformer from 02.10.2020. till 15.10.2020. |
| 8. | Spare parts for transformers | 1 set |  |  | EUR | From 01.06.2020. till 12.06.2020. |

tiek izteiktas šādā redakcijā:

are amended as follows:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Nr. No. | NosaukumsDescription | DaudzumsQuantity | Vienības cenaUnit price | Kopējā cena Total price | ValūtaCurrency | Jāpiegādā /Time schedule |
| 6. | Transformers placing on the foundations after delivery, aggregates assembly, transformers attaching to foundations, connections of secondary equipment, tests of fully assembled transformer and reports of performed tests and commissioning. | 2 units |  |  |  | First transformer from 05.04.2021. till 19.04.2021. |
| Second transformer from 20.09.2021. till 04.10.2021. |
| 7. | 115/21/6.3 kV 25/25/25 MVA transformer - including transformer oil and aggregates. | 2 units |  |  |  | First transformer from 05.04.2021. till 19.04.2021. |
| Second transformer from 20.09.2021. till 04.10.2021. |
| 8. | Spare parts for transformers | 1 set |  |  |  | From 05.04.2021. till 19.04.2021. |

**Grozījums Nr.4**

**Amendment No 4**

Pielikums Nr.6 "Līguma projekts" 3.2. punkts:

Annex 6 "Draft of Contract" Clause 3.2:

|  |  |
| --- | --- |
| 3.2. Preču piegādei un Pakalpojumu izpildei saskaņā ar Līgumu jābūt pabeigtai līdz 2020. gada 2. oktobrim. | 3.2. The supply of Goods and the performance of Services under this Contract shall be concluded until October 2, 20120. |

tiek izteikts šādā redakcijā:

is amended as follows:

|  |  |
| --- | --- |
| 3.2. Preču piegādei un Pakalpojumu izpildei saskaņā ar Līgumu jābūt pabeigtai līdz 2021. gada 4. oktobrim. | 3.2. The supply of Goods and the performance of Services under this Contract shall be concluded until October 4, 2021. |

Šis pielikums ir sarunu procedūras Nr.AST2019/32 nolikuma sastāvdaļa.

This addendum is part of the Regulations of negotiation procedure No.AST2019/32.

SASKAŅOTS/ COORDINATED:

17.04.2019. protokols Nr.1/ minutes No.1

Juris Gavronskis +371 67725235